## Plan
Block | Seq | Code | Item | Platform | Institution | Credits | Start | End | Prerequisites | Status | Hold Reason | Approval | Challenges | Milestones | Touchstones | Tasks | Kind | Student Note | Staff Note | Plan Key
Architecture | 1 |  | Degree architecture review with advisor |  |  |  | 2026-11-02 | 2026-11-13 |  |  |  | Approved |  |  |  |  | Task | Your advisor confirmed the degree architecture. |  | a-arch-review
Architecture | 2 |  | Credit mapping sign-off |  |  |  | 2026-11-09 | 11/20/2026 | a-arch-review |  |  | Pending |  |  |  |  | Task |  | Registrar sign-off outstanding. | a-credit-map
Controlled execution: foundations | 3 | MATH-151 | Calculus I | Study.com | Pathways State University | 4 | 11/23/2026 | 2027-01-10 | a-credit-map |  |  | Pending |  |  |  | Touchstone 1; Final Exam |  |  |  | a-calc-1
Controlled execution: foundations | 4 | MATH-152 | Calculus II | Study.com | Pathways State University | 4 | 2027-01-11 | 2027-02-28 | MATH-151 | [6 empty] | Touchstone 1; Final Exam |  |  |  | a-calc-2
Controlled execution: foundations | 5 | MATH-253 | Calculus III | Study.com | Pathways State University | 4 | 2027-03-01 | 2027-04-18 | MATH-152 | Hold | Only released after the Calculus II provider exam is verified. | [8 empty] | a-calc-3
Controlled execution: advanced | 6 | MATH-301 | Differential Equations | Study.com | Pathways State University | 3 | 2027-04-19 | 5/30/2027 | MATH-253 | [10 empty] | a-diffeq
Controlled execution: foundations | 7 | PHYS-201 | Physics I | Sophia | Pathways State University | 4 | 1/11/2027 | 2027-02-21 |  |  |  | Pending | 6 | 4 | 2 |  |  |  |  | a-physics-1
Controlled execution: advanced | 8 | PHYS-202 | Physics II | Sophia | Pathways State University | 4 | Mar 2027 | 2027-04-11 | a-physics-1, a-calc-2 |  |  |  | 6 | 4 | 2 |  |  |  |  | a-physics-2
Controlled execution: advanced | 9 | STAT-250 | Applied Statistics | Sophia | Pathways State University | 3 | 2027-04-12 | 2027-05-09 |  |  |  |  | 5 | 3 | 1 |  |  |  |  | a-stats
Controlled execution: advanced | 10 | PHIL-210 | Engineering Ethics | Study.com | Pathways State University | 3 |  |  |  | Hold | Provider course availability not yet confirmed. | [8 empty] | a-ethics-hold
Controlled execution: advanced | 11 | EXIT-1 | Program exit assessment |  | Pathways State University |  | 6/1/2027 | 2027-06-12 | a-diffeq, a-physics-2, a-stats |  |  | Pending |  |  |  |  | Exam |  |  | a-final-exam

## Objectives
Key | Title | Kind | Institution | Credential | Status | Note
primary | Bachelor of Science in Applied Sciences | Primary | Pathways State University | BS

## Milestones
Key | Title | Kind | Target Date | Objective | After
a-architecture-done | Architecture approved | checkpoint | 2026-11-20 |  | a-arch-review, a-credit-map
a-degree-complete | Applied sciences degree complete | objective_complete | 2027-06-30 | primary | a-arch-review, a-credit-map, a-calc-1, a-calc-2, a-diffeq, a-physics-1, a-physics-2, a-stats, a-final-exam

## About
Label | Value
Plan Title | Scenario A — controlled execution plan
Summary | Degree architecture first, then controlled, dependency-ordered provider execution.
Primary Degree | Bachelor of Science in Applied Sciences
Institution | Pathways State University
Prepared by | Synthetic fixture builder (not an institutional document)