## Roadmap
Block | Goal | Seq | Code | Item | Provider | Institution | Credits | Planned Start | Target End | Depends On | Status | Approval | Challenges | Milestones | Touchstones | Kind | Student Note | Staff Note | Plan Key
Foundations | Bachelor of Science in Accounting (CPA track) | 1 | ACCT-101 | Financial Accounting | Sophia | Pathways State University | 3 | 2026-11-02 | 2026-11-29 |  |  |  | 5 | 4 | 2 |  |  |  | e-fin-acct
Foundations | bsba | 2 | ECON-101 | Principles of Macroeconomics | Sophia | Pathways State University | 3 | 2026-11-02 | 12/6/2026 |  |  |  | 5 | 4 | 2 |  |  |  | e-econ-mac
Foundations | Bachelor of Science in Business Administration | 4 | MGT-201 | Principles of Management | Sophia | Pathways State University | 3 |  |  |  | Dropped |  | 4 | 3 | 1 |  |  | Dropped after the objective change to Accounting. | e-mgmt
Business core | bs-accounting | 5 | BUS-220 | Business Law | Study.com | Pathways State University | 3 | 2027-01-11 | 2027-02-14 | [9 empty] | e-bus-law
Business core | Bachelor of Science in Business Administration | 6 | STAT-210 | Introduction to Statistics | Sophia | Pathways State University | 3 | 2027-01-11 | 2027-02-14 |  |  |  | 6 | 4 | 2 |  |  |  | e-stats
Business core | bsba | 7 | BUS-310 | Business Communication | Sophia | Pathways State University | 3 | 2027-02-15 | 3/14/2027 |  |  |  | 4 | 3 | 1 |  |  |  | e-bus-comm
Accounting core | Bachelor of Science in Accounting (CPA track) | 8 | ACCT-201 | Managerial Accounting | Sophia | Pathways State University | 3 | 3/18/2027 | 2027-04-14 | e-fin-acct |  |  | 5 | 4 | 2 |  |  |  | e-mgr-acct
Accounting core | bs-accounting | 9 | ACCT-301 | Intermediate Accounting I | Study.com | Pathways State University | 3 | 2027-04-15 | 2027-05-30 | e-fin-acct, e-mgr-acct | [8 empty] | e-int-acct-1
Accounting core | Bachelor of Science in Accounting (CPA track) | 10 | ACCT-302 | Intermediate Accounting II | Study.com | Pathways State University | 3 | 2027-05-31 | 2027-07-11 | e-int-acct-1 | [8 empty] | e-int-acct-2
Accounting core | bs-accounting | 11 | ACCT-410 | Auditing | Study.com | Pathways State University | 3 | 2027-07-12 | 8/22/2027 | e-int-acct-2 | [8 empty] | e-audit
Accounting core | Bachelor of Science in Accounting (CPA track) | 12 | ACCT-420 | Federal Taxation | Study.com | Pathways State University | 3 | 7/12/2027 | 2027-08-22 | e-int-acct-1 | [8 empty] | e-tax
CPA planning | bs-accounting | 13 |  | CPA licensure planning: state board credit and course-content review |  | Pathways State University |  | 2026-12-06 | 2027-01-15 |  |  | Pending |  |  |  | Task | We will check the state board's requirements with you before you register for accounting courses. |  | e-cpa-planning
CPA planning | Bachelor of Science in Accounting (CPA track) | 14 |  | State board exam eligibility application |  | Pathways State University |  | 2027-09-01 | 2027-09-30 | e-audit, e-tax, e-cpa-planning |  | Pending |  |  |  | Application |  |  | e-cpa-app

## Objectives
Key | Title | Kind | Institution | Credential | Status | Note
bs-accounting | Bachelor of Science in Accounting (CPA track) | Primary | Pathways State University | BS |  | Objective changed with advisor approval in October 2026.
bsba | Bachelor of Science in Business Administration | Secondary | Pathways State University | BS | Changed | Previous objective, kept for history.

## Milestones
Key | Title | Kind | Target Date | Objective | After
e-acct-core-done | Accounting core complete | checkpoint | 2027-08-15 | bs-accounting | e-mgr-acct, e-int-acct-1, e-int-acct-2, e-audit, e-tax
e-cpa-eligibility | CPA exam eligibility application | application | 2027-09-30 | bs-accounting | e-cpa-app

## About
Label | Value
Plan Title | Scenario E — Accounting (CPA track) plan
Summary | Objective changed to Accounting with CPA licensure planning. The earlier Business Administration objective is kept as history.
Primary Degree | Bachelor of Science in Accounting (CPA track)
Institution | Pathways State University
Prepared by | Synthetic fixture builder (not an institutional document)